## Sheet1
Time | Mario | Tobias | Radu | Nikita | Max | Manvydas | Tolga
Week 1 | Top | Pump | Pump | Top/Bottom | Bottom | Nextion | Nextion
Week 2 | Top | Pump | Pump | Top/Bottom | Bottom | Nextion | Nextion
Week 3
Week 4
Week 5
Week 6
Week 7
Week 8
Week 9
Week 10
Week 11
Week 12
Week 13
Week 14
2025-03-18
· Pump
Failed test.
The glue failed above 10 PSI of pressure.
Suggested solution: Maka a metal container and weld a threaded hole to it.
· Screen
Task successfull
X and y extraction
New task: Octocupler code
· X axis motor
NX model done
Building/Programing servo motors
· Y axis motor
NX model done
NX model of all components
2025-03-25
· Pump
New pressure tank succesful up to 150 PSI
Testing with water for next time
Still waiting on the metal container
· Screen
Wrote state changing code
To be tested during meeting on the screen
· X axis motor
Waiting for materials
· Y axis motor
Waiting for materials
· Electrical Pump
Soldering the wires and testing distance of new electric pump
During the meeting