## Sheet1
Time | Mario | Tobias | Radu | Nikita | Max | Manvydas | Tolga
Week 1 | Top | Pump | Pump | Top/Bottom | Bottom | Nextion | Nextion
Week 2 | Top | Pump | Pump | Top/Bottom | Bottom | Nextion | Nextion
Week 3
Week 4
Week 5
Week 6
Week 7
Week 8
Week 9
Week 10
Week 11
Week 12
Week 13
Week 14
2025-03-18
· Pump
Failed test.
The glue failed above 10 PSI of pressure.
Suggested solution: Maka a metal container and weld a threaded hole to it.
· Screen
Task successfull
X and y extraction
New task: Octocupler code
· X axis motor
NX model done
Building/Programing servo motors
· Y axis motor
NX model done
NX model of all components
2025-03-25
· Pump
New pressure tank succesful up to 150 PSI
Testing with water for next time
Still waiting on the metal container
· Screen
Wrote state changing code
To be tested during meeting on the screen
· X axis motor
Waiting for materials
· Y axis motor
Waiting for materials
· Electrical Pump
Soldering the wires and testing distance of new electric pump
During the meeting
2025-04-01
· Pump
We found out that the barometer we ordered was only rated for much lower pressures
3D printed pressure tank does not have enough walls
Starting print on 3rd itteration with more walls
· Screen
Modified state changing code to use functions instead (due to NX display issues
Not tested yet
· X axis motor
Nothing to do because the mottor did not arive yet
· Y axis motor
Nothing to do because no motor yet
Measuring electric pump and making a model on NX
· Electrical Pump
Testing the pump
During the meeting
Very underwealming results